## Sheet1
Sr. No | Bug Description | Assignee | Severity | Reporter | Start Date | End Date | Status | Developer comment
1 | Unable to login after searching for rooms. | Snehal |  | Sujay Sir | 2016-09-02 | 2016-10-02 | Resolved
2 | Login window is distorted. | Mukesh |  | Sujay Sir | 9/2/2016 | 2016-09-02 | Resolved
3 | Unable to login with admin/admin | Snehal |  | Sujay Sir | 2016-09-02 | 2016-10-02 | Resolved
4 | Validation on search is still pending. Still able to search using past dates. | Snehal |  | Sujay Sir | 9/2/2016 | 2016-11-02 | Resolved
5 | Every search result shows 2 unwanted texts as shown below. This text is shown with or without any results. They are no hyperlinks or linked with any property. Remove them $4,650 $2,650 Best price | Shruti |  | Sujay Sir | 2016-09-02 | 2016-09-02 | Resolved
6 | Search filters are not aligned properly. Each search section must same height for title. Reduce height for all headers in like Name contains, Per night rate, etc. | Shruti/Mukesh |  | Sujay Sir | 2016-09-02 | 2016-10-02 | Resolved
7 | Check boxes shown in search filters must also have equal spacing. For Star rating there is spacing between check box and rating. But for Features, there is no spacing. Reduce spacing and height of each Star rating sections check box. Same height and spacing must be given to all filter options. | Mukesh |  | Sujay Sir | 2016-09-02 | 2016-10-02 | Resolved | a
8 | 8. Facilites Filter section - a. There is additional dot before "Accomodation type". b. Accomodation type is shown with collapsible link, on click nothing happens. c. Options must be shwon as check boxes instead of links. This way user can select/deselect a option. Make sure same style is applied for all sections. | Snehal |  | Sujay Sir | 2016-09-02 | 2016-11-02 | Resolved
9 | Click on "Continue" : nothing happens - http://propertybook.agilesoftsol.com/single.html | Snehal |  | Sujay Sir | 2016-09-02 | 2016-12-02 | Resolved
10 | After I open a property from property search, i see name of vishwanath at the end of the page without any context. Like is open "Vg Homes". | Snehal |  | Sujay Sir | 2016-09-02 | 2016-09-02 | Resolved
11 | Send mail form a. Form have too much spacing. b. Label and fields are not aligned c. Date fields doesnt show popup in aligned with field. d. Unable to select date. e. Show a bigger Enquiry text area. f. Weired message alert is shown on send button - "from here it will get to piyu mney" | Snehal/Mukesh |  | Sujay Sir | 2016-09-02 | 2016-10-02 | Resolved
12 | Send SMS a. Form have too much spacing. b. Label and fields are not aligned c. Title of the popup should be "Send SMS" instead of "Enquiry via email" d. Weired message alert is shown on send button - "from here it will get to piyu mney" | Snehal/Mukesh |  | Sujay Sir | 2016-09-02 | 2016-10-02 | Resolved
13 | 1. In property search page - when i select any check box, i get alert - "Message sent succesfully". Remove such development messages in SVN | Snehal |  | Sujay Sir | 15/2/2016 | 15/2/2016 | Resolved
14 | Accomodations name must be proper - 1bhk should be 1 BHK | Shruti |  | Sujay Sir | 15/2/2016 | 15/2/2016 | Resolved
15 | Reduce the height and spacing of Star rating. Taking a bit more space. | Mukesh |  | Sujay Sir | 15/2/2016 | 15/2/2016 | Resolved
16 | Make all Sections expanded at same time currently only one section can be seen. | Mukesh |  | Sujay Sir | 15/2/2016 | 15/2/2016
17 | On home page Search bar is shown after the image instead of above.Also it is not changing the look and feel to original needs | Snehal |  | Sujay Sir | 15/2/2016 | 15/2/2016 | Resolved
18 | Reduce the height of first 4 sections shown in property search | Mukesh |  | Sujay Sir | 15/2/2016 | 15/2/2016 | Resolved